**Master-Project Timeline**

Deliverance Bougie

Stefan Zimmerman

3 February 2022

* Deliverable 1: 3 February 2022
  + Timeline
    - Submit timeline for thesis project
  + Data Access
    - Obtain access to the necessary SOEP survey data
  + Variable Selection
    - Identify variables that will be used for project
  + Data Import
    - Load (and merge?) datasets with selected variables
* Deliverable 2: 3 March 2022
  + Begin Data Wrangling
    - Rename variables
    - Format data
  + Data Exploration
    - Summary statistics
    - Visualizations
  + Generate Tables
    - Tables of aggregate data used for dashboard
  + Data Quality Checks
    - Check quality of record linkage (?)
    - Identify and resolve missing data
    - Review summary statistics and visualizations for potential data quality issues
    - More data wrangling if necessary
* Deliverable 3: 31 March 2022
  + Regression models
  + Design Dashboard
  + Dashboard Inputs
* Deliverable 4: 28 April 2022
  + Dashboard Testing
  + Metadata
    - Identify documentation added to dashboard
* Deliverable 5: 2 June 2022
  + Finalize Dashboard
  + Finalize Metadata
  + Draft of Written Component